## Sheet1
Phases | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Alignment | Alignment with Risk, Compliance, and Legal teams | bar: 1
Review TOM with input from the Technology Organization | bar: 2
Finalize TOM | bar: 3
Publish TOM | bar: 4
Assess | Review Baseline of Existing Data Governance | bar: 5
Conduct Gap Analysis | bar: 6
Conduct Stakeholer Workshops to Address Gaps | bar: 7
Align Final Action Plan with Delivery Teams | bar: 8
Build | Consolidate Information into a Centralized Database | bar: 9
Decommission Redundant Servers and Datasets | bar: 9
Finalize the configuration of the centralized database | bar: 10
Conduct system integration tests to ensure smooth data flow | bar: 11
Begin the pilot phase of the new access controls | bar: 12
Roll-out | Implement secure database access for all user groups | bar: 13
Provide advanced training for high-risk data handlers | bar: 14
Complete full-scale rollout of secure access controls | bar: 15
Finalize all documentation and close out the project | bar: 16
Ensure that ongoing monitoring mechanisms are in place | bar: 16

## Sheet2
| Fully Compliant | Partially Compliant | Non-Compliant
Gartner | 73.8% | 12.9% | 13.3%
GDPR | 71.2% | 14.5% | 14.3%
HIPPA | 67.8% | 16.5% | 15.7%
ISO 27001 | 83.2% | 9.4% | 7.4%
74%