## Sheet1
8. Sample Test Cases:
Test Case |  | Input Data | Expected Output
ID | Test Case Description
TC-OOI | Data retrieval from provider | N/A | Successful data retrieval
TC-002 | Handling missing data | Dataset with missing values | Correctly imputed or removed missing values
TC-003 | Feature engineeri ng calculation | Raw dataset | Correctly calculated features
TC-004 | LSTM model training | Preprocessed training dataset | Model with expected training accuracy
TC-005 | Short-term price prediction | Preprocessed test dataset | Predicted OHLC prices with acceptable accuracy
TC-006 | End-to-end workflow | Complete dataset | Successful data processing and prediction
TC-007 TC-008 | Risk managernent integration Performance metrics calculation | Trading strategy Predicted and actual prices | Correct application of stop-loss and srnng Accurate calculation of performance metrics
TC-009 | User scenario simulation | Live market data (simulation) | Successful execution and feedback collection

## Sheet2
Weeks | Deliverables | Completion Dates | Status
1 | Publish Project Charter | 2024-06-24 | Completed
1.1 | Define Project Scope and Objectives
1.2 | Outline Project Deliverables
2 | Set-up Live-Data Extraction System | 2024-07-01 | In-Progress
3 | Conduct the Exploratory Data Analysis | 2024-07-08 | Planned
3.1 | Perform Initial Data Analysis
3.2 | Visulaize Data Distributions and Trends
3.3 | Identify any Data Quality Issues
4 | Pre-process Data for Moedlling | 2024-07-15 | Planned
4.1 | Engineer New Features
4.2 | Normalize Data
5 | Explore Modelling Techniques | 2024-07-22 | Planned
5.1 | Evaluate different deep learning models (LSTM, CNN, Transformers)
5.2 | Perform model comparison
5.3 | Document findings and insights
6 | Identify the Best Model | 2024-07-29 | Planned
6.1 | Fine-tune hyperparameters of selected models
6.2 | Validate models on validation dataset
6.3 | Select the best performing model
7 | Deploy the Best Model | 2024-08-05 | Planned
7.1 | Deploy model in live trading environment
7.2 | Monitor model performance
7.3 | Make necessary adjustments based on live data feedback
8 | Report Progress | 2024-08-12 | Planned
8.1 | Compile project progress and results
8.2 | Present Progress
Formulas:
Completion Dates = [Completion Dates, row above]+7